## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  | QUARTER: | 1
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Improvement of Satellite Market, San Antonio Satellite Market @ Brgy. Binabag, Bogo City | Binabag | 20572761.97 | 2021-08-16 | 2022-06-30 | 99.99% | 20570569.86 |  | COMPLETED
Installation of Water Distribution Line to Sitio Calubian & Japitana, Brgy. Don Pedro | Don Pedro | 998418 | 2021-11-01 | 2022-07-31 | 99.71% | 995517 |  | COMPLETED
Construction of Multipurpose Building (Phase 2) | Pandan | 2496484.4 | 2022-03-22 | 2022-10-17 | 100% | 2496484.4 |  | COMPLETED
Economic Development (pls list down specific projects)
Construction/Improvement/Upgrading of Baas-Dakit Road | Baas-Dakit | 22793849.35 | 2022-04-25 | 2023-03-30 | 100% | 22793849.35 |  | COMPLETED
Road Rehabilitation & Improvement & Site Preparation | Bogo City | 15032219.24 | 2022-06-01 | 2023-02-02 | 100% | 15032219.24 |  | COMPLETED
Construction of Drainage for N. Lepite St., Gairan, Sitio Liloy, Banban & Sto. Rosario | various | 1999271.6 | 2022-11-12 | 2023-09-01 | 81% | 1619339 |  | ON-GOING
Rehabilitation of New Public Market (Bogo Public Market) | Gairan | 1810375 | 2022-08-03 | 2022-12-30 | 99.96% | 1809635 |  | COMPLETED
Improvement of Polambato Port (Phase 4) | Polambato | 28006726.8 | 2022-03-22 | 2022-07-19 | 99.92% | 27984250 |  | COMPLETED
improvement of slaughterhouse Office | Gairan | 469798 | 2022-07-04 | 2023-05-30 | 99.92% | 469402 |  | COMPLETED
Construction of One (1) Storey New Commercial Public Market Buildings | Gairan | 33803219.95 | 2021-11-03 | 2023-05-02 | 73.39% | 24806528.67 |  | ON-GOING
Fabrication of Roofing & Concreting of Oil Depot Area | Sitio Maharat, Bungtod | 232749 | 2023-02-13 | 2023-05-19 | 18.56% | 43200 |  | ON-GOING
Environmental Management (pls list down specific projects)
Site Development of Propose Cemetery (P1) | Malingin | 336708 | 2022-05-23 | 2022-12-31 | 78.05% | 262800 |  | ON-GOING
Weel Exploration for NHA Water Supply | Banban | 328090 | 2022-10-26 | 2023-06-30 | 20.63% | 67690 |  | ON-GOING
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Atty. Jose Neil D. Lumongsod, CPA | [5 empty] | Atty. Carlo Jose A. Martinez
Local Accountant | [5 empty] | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2