## 1st Q
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: VII |  |  | CALENDAR YEAR: | 2023
PROVINCE: CEBU |  |  | QUARTER: | 1
CITY/MUNICIPALITY: BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Installation, Transmission & Distribution of Water Pipeline | Bogo City | 1999999.7 | 2022-02-07 | 2022-12-31 | 67.69% | 1353700 |  | on-going
Construction of Extended Roofing at the Evacuation Center | Brgy. Dakit | 578980.25 | 2022-03-01 | 2022-12-31 | 99.14% | 574022.36 |  | on-going
Construction of Brgy. DRRM Office | Bogo City | 384516.96 | 2022-03-01 | 2022-12-31 | 0% |  |  | documents for review
Rehabilitation of Multi-purpose & Evacuation Center (Phase V) | Brgy. Lapaz | 500000 | 2022-03-01 | 2022-12-31 | 59.85% | 299256.25 |  | on-going
Construction of Multi-purpose Activity Center (Phase 1) | Brgy. A. Norte | 500000 | 2022-03-01 | 2022-12-31 | 85.8% | 429008.58 |  | on-going
Bogo Water District Water Utilities Meterstand Transfer & Installation
of UPVC | Bogo City | 3000000 |  |  | 0% |  |  | documents for review
Binabag Water System | Brgy. Binabag | 5000000 |  |  | 0% |  |  | documents for review
Polambato Development Port (Phase V) | Brgy. Polambato | 30000000 | 2022-07-19 | 2022-12-16 | 16.14% | 4841182.5 |  | on-going
Concreting of Cogon-Pandan Road | Bogo City | 19572700 | 2022-12-06 | 2023-05-15 | 27.28% | 5338900.66 |  | on-going
Installation of Streetlights Along National & City Road | Bogo City | 15000000 | 2022-09-06 | 2023-02-23 | 18.28% | 2741665.9 |  | on-going
PTO-Various items claimed for Sugbo Negosyo Program | Bogo City | 603860.88 |  |  | 0% |  |  | documents for review
PTO-Sugbo Negosyo Program | Bogo City | 923766.18 |  |  | 0% |  |  | documents for review
PTO-Various Infra : Two Storey Classroom Bldg. SHS, Cogon, Bogo | Bogo City | 6997202.32 |  |  | 0% |  |  | documents for review
PTO-Various Infra: Road Opening, Jovencio Masong Nat'l HS | Nailon, Bogo | 3000000 |  |  | 0% |  |  | documents for review
PTO-Suroy-suroy Sa Sugbo Northern Escapade | Bogo City | 500000 |  |  | 0% |  |  | documents for review
DOH-Implementation of Health Emergency Management | Bogo City | 500000 |  |  | 0% |  |  | documents for review
DOH-Community Base Treatment Rehab Facility | Bogo City | 500000 |  |  | 0% |  |  | documents for review
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive

## 2nd Q
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: VII | [5 empty] | CALENDAR YEAR: | 2023
PROVINCE: CEBU | [5 empty] | QUARTER: | 1
CITY/MUNICIPALITY: BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Installation, Transmission & Distribution of Water Pipeline | Bogo City | 1999999.7 | 2022-02-07 | 2022-12-31 | 73.69% | 1473700 |  | on-going
Construction of Extended Roofing at the Evacuation Center | Brgy. Dakit | 578980.25 | 2022-03-01 | 2022-12-31 | 99.14% | 574022.36 |  | on-going
Construction of Brgy. DRRM Office | Bogo City | 384516.96 | 2022-03-01 | 2022-12-31 | 0% |  |  | documents for review
Rehabilitation of Multi-purpose & Evacuation Center (Phase V) | Brgy. Lapaz | 500000 | 2022-03-01 | 2022-12-31 | 59.85% | 299256.25 |  | on-going
Construction of Multi-purpose Activity Center (Phase 1) | Brgy. A. Norte | 500000 | 2022-03-01 | 2022-12-31 | 85.8% | 429008.58 |  | on-going
Bogo Water District Water Utilities Meterstand Transfer & Installation
of UPVC | Bogo City | 3000000 |  |  | 0% |  |  | documents for review
Binabag Water System | Brgy. Binabag | 5000000 |  |  | 0% |  |  | documents for review
Polambato Development Port (Phase V) | Brgy. Polambato | 30000000 | 2022-07-19 | 2022-12-16 | 99.9% | 29969150 |  | on-going
Concreting of Cogon-Pandan Road | Bogo City | 19572700 | 2022-12-06 | 2023-05-15 | 60.99% | 11937662.1 |  | on-going
Installation of Streetlights Along National & City Road | Bogo City | 15000000 | 2022-09-06 | 2023-02-23 | 62.15% | 9321905.7 |  | on-going
PTO-Various items claimed for Sugbo Negosyo Program | Bogo City | 603860.88 |  |  | 0% |  |  | documents for review
PTO-Sugbo Negosyo Program | Bogo City | 923766.18 |  |  | 0% |  |  | documents for review
PTO-Various Infra : Two Storey Classroom Bldg. SHS, Cogon, Bogo | Bogo City | 6997202.32 |  |  | 0% |  |  | documents for review
PTO-Various Infra: Road Opening, Jovencio Masong Nat'l HS | Nailon, Bogo | 3000000 | 2023-01-22 | 2023-06-30 | 99.96% | 2998800.45 |  | on-going
PTO-Suroy-suroy Sa Sugbo Northern Escapade | Bogo City | 500000 | 2023-01-22 | 2023-10-20 | 48% | 240000 |  | on-going
DOH-Implementation of Health Emergency Management | Bogo City | 500000 |  |  | 0% |  |  | documents for review
DOH-Community Base Treatment Rehab Facility | Bogo City | 500000 |  |  | 0% |  |  | documents for review
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Atty. Jose Neil D. Lumongsod, CPA | [5 empty] | Atty. Carlo Jose A. Martinez
Local Accountant | [5 empty] | Local Chief Executive

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2