## 1st Q (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  | QUARTER: | 1
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Improvement of Satellite Market, San Antonio Satellite Market @ Brgy. Binabag, Bogo City | Binabag | 20572761.97 | 2021-08-16 | 2022-06-30 | 99.99% | 20570569.86 |  | COMPLETED
Installation of Water Distribution Line to Sitio Calubian & Japitana, Brgy. Don Pedro | Don Pedro | 998418 | 2021-11-01 | 2022-07-31 | 99.71% | 995517 |  | COMPLETED
Construction of Multipurpose Building (Phase 2) | Pandan | 2496484.4 | 2022-03-22 | 2022-10-17 | 100% | 2496484.4 |  | COMPLETED
Economic Development (pls list down specific projects)
Construction/Improvement/Upgrading of Baas-Dakit Road | Baas-Dakit | 22793849.35 | 2022-04-25 | 2023-03-30 | 100% | 22793849.35 |  | COMPLETED
Road Rehabilitation & Improvement & Site Preparation | Bogo City | 15032219.24 | 2022-06-01 | 2023-02-02 | 100% | 15032219.24 |  | COMPLETED
Construction of Drainage for N. Lepite St., Gairan, Sitio Liloy, Banban & Sto. Rosario | various | 1999271.6 | 2022-11-12 | 2023-09-01 | 81% | 1619339 |  | ON-GOING
Rehabilitation of New Public Market (Bogo Public Market) | Gairan | 1810375 | 2022-08-03 | 2022-12-30 | 99.96% | 1809635 |  | COMPLETED
Improvement of Polambato Port (Phase 4) | Polambato | 28006726.8 | 2022-03-22 | 2022-07-19 | 99.92% | 27984250 |  | COMPLETED
improvement of slaughterhouse Office | Gairan | 469798 | 2022-07-04 | 2023-05-30 | 99.92% | 469402 |  | COMPLETED
Construction of One (1) Storey New Commercial Public Market Buildings | Gairan | 33803219.95 | 2021-11-03 | 2023-05-02 | 73.39% | 24806528.67 |  | ON-GOING
Fabrication of Roofing & Concreting of Oil Depot Area | Sitio Maharat, Bungtod | 232749 | 2023-02-13 | 2023-05-19 | 18.56% | 43200 |  | ON-GOING
Environmental Management (pls list down specific projects)
Site Development of Propose Cemetery (P1) | Malingin | 336708 | 2022-05-23 | 2022-12-31 | 78.05% | 262800 |  | ON-GOING
Weel Exploration for NHA Water Supply | Banban | 328090 | 2022-10-26 | 2023-06-30 | 20.63% | 67690 |  | ON-GOING
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Local Budget Officer |  |  |  | Local Chief Executive

## 1st Q (2) (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  | QUARTER: | 1
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Improvement of Satellite Market, San Antonio Satellite Market @ Brgy. Binabag, Bogo City | Binabag | 20572761.97 | 2021-08-16 | 2022-06-30 | 99.99% | 20570569.86 |  | COMPLETED
Installation of Water Distribution Line to Sitio Calubian & Japitana, Brgy. Don Pedro | Don Pedro | 998418 | 2021-11-01 | 2022-07-31 | 99.71% | 995517 |  | COMPLETED
Construction of Multipurpose Building (Phase 2) | Pandan | 2496484.4 | 2022-03-22 | 2022-10-17 | 100% | 2496484.4 |  | COMPLETED
Economic Development (pls list down specific projects)
Construction/Improvement/Upgrading of Baas-Dakit Road | Baas-Dakit | 22793849.35 | 2022-04-25 | 2023-03-30 | 100% | 22793849.35 |  | COMPLETED
Road Rehabilitation & Improvement & Site Preparation | Bogo City | 15032219.24 | 2022-06-01 | 2023-02-02 | 100% | 15032219.24 |  | COMPLETED
Rehabilitation of New Public Market (Bogo Public Market) | Gairan | 1810375 | 2022-08-03 | 2022-12-30 | 99.96% | 1809635 |  | COMPLETED
Improvement of Polambato Port (Phase 4) | Polambato | 28006726.8 | 2022-03-22 | 2022-07-19 | 99.92% | 27984250 |  | COMPLETED
improvement of slaughterhouse Office | Gairan | 469798 | 2022-07-04 | 2023-05-30 | 99.92% | 469402 |  | COMPLETED
Construction of One (1) Storey New Commercial Public Market Buildings | Gairan | 33803219.95 | 2021-11-03 | 2023-05-02 | 73.39% | 24806528.67 |  | ON-GOING
Fabrication of Roofing & Concreting of Oil Depot Area | Sitio Maharat, Bungtod | 232749 | 2023-02-13 | 2023-05-19 | 18.56% | 43200 |  | ON-GOING
Environmental Management (pls list down specific projects)
Site Development of Propose Cemetery (P1) | Malingin | 336708 | 2022-05-23 | 2022-12-31 | 78.05% | 262800 |  | ON-GOING
Weel Exploration for NHA Water Supply | Banban | 328090 | 2022-10-26 | 2023-06-30 | 20.63% | 67690 |  | ON-GOING
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Local Budget Officer |  |  |  | Local Chief Executive

## 2nd Q (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  | QUARTER: | 2
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Economic Development (pls list down specific projects)
Supply & Delivery of Streetlights with Installation | Bogo City | 16623142.22 | 2023-04-20 | 2023-10-07 | 81.64% | 13571666.49 |  | ON-GOING
Road Concreting of Brgy. Marangog - Odlot via Sitio Tagasa | Marangog | 26101530.95 | 2023-05-31 | 2023-12-26 | 90.42% | 23600010.6 |  | ON-GOING
Construction of Drainage for N. Lepite St., Gairan, Sitio Liloy, Banban & Sto. Rosario | various | 1999271.6 | 2022-11-12 | 2023-09-01 | 81% | 1619339 |  | ON-GOING
improvement of slaughterhouse Office | Gairan | 469798 | 2022-07-04 | 2023-05-30 | 99.92% | 469402 |  | COMPLETED
Construction of One (1) Storey New Commercial Public Market Buildings | Gairan | 33803219.95 | 2021-11-03 | 2023-05-02 | 73.39% | 24806528.67 |  | ON-GOING
Fabrication of Roofing & Concreting of Oil Depot Area | Sitio Maharat, Bungtod | 232749 | 2023-02-13 | 2023-05-19 | 18.56% | 43200 |  | ON-GOING
Environmental Management (pls list down specific projects)
Site Development of Propose Cemetery (P1) | Malingin | 336708 | 2022-05-23 | 2022-12-31 | 78.05% | 262800 |  | ON-GOING
Weel Exploration for NHA Water Supply | Banban | 328090 | 2022-10-26 | 2023-06-30 | 20.63% | 67690 |  | ON-GOING
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Atty. Jose Neil D. Martinez, CPA |  |  |  | Atty. Carlo Jose A. Martinez
| Local Accountant |  |  |  | Local Chief Executive

## 2nd Q (2) (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  | QUARTER: | 2
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Economic Development (pls list down specific projects)
Supply & Delivery of Streetlights with Installation | Bogo City | 16623142.22 | 2023-04-20 | 2023-10-07 | 81.64% | 13571666.49 |  | ON-GOING
Road Concreting of Brgy. Marangog - Odlot via Sitio Tagasa | Marangog | 26101530.95 | 2023-05-31 | 2023-12-26 | 90.42% | 23600010.6 |  | ON-GOING
improvement of slaughterhouse Office | Gairan | 469798 | 2022-07-04 | 2023-05-30 | 99.92% | 469402 |  | COMPLETED
Construction of One (1) Storey New Commercial Public Market Buildings | Gairan | 33803219.95 | 2021-11-03 | 2023-05-02 | 73.39% | 24806528.67 |  | ON-GOING
Fabrication of Roofing & Concreting of Oil Depot Area | Sitio Maharat, Bungtod | 232749 | 2023-02-13 | 2023-05-19 | 18.56% | 43200 |  | ON-GOING
Environmental Management (pls list down specific projects)
Site Development of Propose Cemetery (P1) | Malingin | 336708 | 2022-05-23 | 2022-12-31 | 78.05% | 262800 |  | ON-GOING
Weel Exploration for NHA Water Supply | Banban | 328090 | 2022-10-26 | 2023-06-30 | 20.63% | 67690 |  | ON-GOING
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Atty. Jose Neil D. Martinez, CPA |  |  |  | Atty. Carlo Jose A. Martinez
| Local Accountant |  |  |  | Local Chief Executive

## 3rd Q (hidden)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  | QUARTER: | 3
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Construction of Multipurpose and Activity Center (Phase 3) | Anonang Norte | 2009025.25 | 2023-08-15 | 2023-09-30 | 92.88% | 1865883.39
Economic Development
Supply & Delivery of Streetlights with Installation | Pandan-Odlot Road, Bogo City | 16623142.22 | 2023-04-20 | 2023-10-07 | 81.64% | 13571666.49 |  | ON-GOING
Road Concreting of Brgy. Marangog - Odlot via Sitio Tagasa | Marangog | 26101530.95 | 2023-05-31 | 2023-12-26 | 90.42% | 23600010.6 |  | ON-GOING
improvement of slaughterhouse Office | Gairan | 469798 | 2022-07-04 | 2023-05-30 | 99.92% | 469402 |  | COMPLETED
Improvement of Polambato Port (Phase 5) Dredging of Berthing Area w/ Disposal | Polambato | 29969150 | 2022-07-19 | 2023-03-13 | 100% | 29969150 |  | COMPLETED
Site Development of Propose Cemetery (P1) | Malingin | 336708 | 2022-05-23 | 2022-12-31 | 78.05% | 262800 |  | ON-GOING
Environmental Management
Well Exploration for NHA Water Supply | Banban | 328090 | 2022-10-26 | 2023-06-30 | 20.63% | 67690 |  | ON-GOING
TOTAL | [5 empty] | 69806602.48
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Atty. Jose Neil D. Lumongsod, CPA |  |  |  | Atty. Carlo Jose A. Martinez
| Local Accountant |  |  |  | Local Chief Executive

## 4th Q
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | VII |  |  |  |  | CALENDAR YEAR: | 2023
PROVINCE: | CEBU |  |  |  |  | QUARTER: | 4
CITY/MUNICIPALITY: | BOGO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Construction of Multipurpose and Activity Center (Phase 3) | Anonang Norte | 2009025.25 | 2023-08-15 | 2023-09-30 | 100% | 2009025.05 |  | COMPLETED
Const. of Multi-purpose Building, Brgy. Marangog (P2) | Marangog | 2727000 | 2023-12-01 | 2024-05-30 | 80.81% | 2203635.99 |  | ON-GOING
Const. of Multi-purpose Building, Brgy. Malingin (P2) | Malingin | 3936000 | 2023-12-01 | 2024-05-30 | 70.2% | 2762921.81 |  | ON-GOING
Construction of Multipurpose Bldg @ Polambato Port (Pasalubong Center) | Polambato | 2833461.5 | 2023-12-01 | 2024-05-30 | 100% | 2833461.5 |  | COMPLETED
Economic Development
Supply & Delivery of Streetlights with Installation | Pandan-Odlot Road, Bogo City | 16623142.22 | 2023-04-20 | 2023-10-07 | 100% | 16623142.22 |  | COMPLETED
Road Concreting of Brgy. Marangog - Odlot via Sitio Tagasa | Marangog | 26101530.95 | 2023-05-31 | 2023-12-26 | 100% | 26101530.955 |  | COMPLETED
Road Concreting of Tolibao-Bung aw Elem. School (w/ exception) | Malingin | 6904435.7 | 2023-11-20 | 2023-12-30 | 100% | 6904435.7 |  | COMPLETED
Road Concreting of Tolibao Road (connecting City-Provincial Road | Malingin | 2821366.72 | 11/01//23 | 2023-12-29 | 100% | 2821366.72 |  | COMPLETED
Road Concreting of Brgy. Malingin Elem. School | Malingin | 29998060.37 | 2023-12-01 | 2024-06-25 | 85.79% | 25733875.91 |  | ON-GOING
Construction of New Public Cemetery, Sitio Langaw, Brgy. Malingin | Malingin | 24998114.22 | 2023-12-01 | 2024-05-30 | 85.19% | 21296496.11 |  | ON-GOING
Environmental Management
TOTAL | [5 empty] | 109289891.965
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Atty. Jose Neil D. Lumongsod, CPA |  |  |  | Atty. Carlo Jose A. Martinez
| Local Accountant |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2